
**Maine Continuum of Care**

**Project Timeline**

On Friday, November 22, 2013, HUD released the Notice of Funding Availability (NOFA) for the Continuum of Care Program Competition.

Mon. Dec. 2, 2013: Steering Committee Meeting with Anne

Gass, Consultant to review the NOFA

Application, its changes and plan to

complete Sections 3 and 4.

Mon. Dec. 9, 2013 Steering Committee Meeting and

Work session with Anne Gass to continue work and set the timeline for goals and objectives

Mon. Dec. 16th, 2013 Project Committee Meeting to review

scoring template in am and Steering

committee in the afternoon

Thu. Dec. 19th, 2013 Maine CoC meeting

Mon. Dec. 30th, 2013 Joint Project and Steering Committee

Meeting at 10:00am-3:00 pm

**Fri. Jan. 3, 2014** **E-SNAPS PROJECT APPLICATION**

(former Exhibit 2) **DEADLINE TO**

**COMPLETE**

Mon. Jan. 6, 2014 Steering Committee Work Session

Mon. Jan. 13, 2014 Steering Committee Work Session

Thu. Jan. 16, 2014 Maine CoC Meeting to finalize and approve

the NOFA application.

**Fri. Jan. 17, 2014** **CoC Notification to Project Applicants**

Thu. Jan 23, 2014 Maine CoC Meeting to finalize and approve

the NOFA application

Mon. Jan. 27, 2014 Steering Committee Work Session to

Complete any unfinished items

**FEBRUARY 3, 2014 GRANT APPLICATION DUE TO HUD**

**(Monday)**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

**FMI:**

Paula Paladino, Manager of Homeless Initiatives: [ppaladino@mainehousing.org](mailto:ppaladino@mainehousing.org) OR

Anne Gass, Grant Consultant, [agass@maine.rr.com](mailto:agass@maine.rr.com)