Maine’s Coordinated Assessment: Next Steps

What We’ll Accomplish in 2014:	Design Phase

- A Coordinated Assessment (CA) Committee, including members of both the Maine and the Portland CoCs, met four times between August and December to:

  - Review HUD requirements for the CA

  - Consider and recommend to the full CoCs for their review, amendments and approval, options for a statewide CA system that would build on existing strengths and resources

- CA Committee members met with the Portland and Maine CoC full memberships in September to present initial recommendations

- In September, applied to the Betterment Fund for a grant to hire a staff person to help implement the CA system. Application was funded and will allow the hiring of a staff person in January/early February.

- The CA Committee will present final recommendations to the CoCs in December.

  - Outline recommendations after CoC meetings

- Finalize in writing the design of Maine’s CA system

- In December, the CoCs should submit proposal to the Elvira Sewall and (possibly) a letter of inquiry to the Sam L Cohen Foundation for their spring rounds.

Next Steps for Maine’s CA System:	Implementation Phase

| January | - Obtain CoC approval of CA recommendations, if not already received at December meeting - Hire a staff person with Betterment Fund award - If invited, proceed with application to Sam L Cohen Foundation (February 1 deadline) - Expand CA Committee membership to include consumers and broader representation from Maine and Portland CoCs and establish (in writing) its authority and decision making process - Key participants: shelter operators, ESG recipients, government officials, CoC lead agencies, funders, housing providers - Identify subcommittees to assist with specific implementation tasks and protocol development |
| --- | --- |
| Jan - June | - Expand data sharing protocols statewide and document timeline for data sharing implementation with each participating program - Require use of HMIS by participating agencies and arrange for licensure - Add functionality required to support CA (CallPoint, empty bed module?, others?) |
| Mar - June | - Develop implementation timeline - Develop budget and identify long term funding - Develop metrics & dashboard for tracking provider and system performance in diversion, access, assessment, and assignment - Identify pilot sites/regions/populations for pilot - Implement pilot, measure and report results |

DETAILED TASK LIST:

- Adopt guiding principles and shared values for Coordinated Assessment system

- Determine scale of coordinated assessment pilot

  - Subpopulation? (Singles, families, etc),

  - Geography area?

  - CA Committee recommends that DV resources and households be phased in a later date

- Set a ‘Go Live’ date

- Develop Policy and Procedure manual for system access, assessment and referral activities

  - Include detailed  steps from initial household interaction through post-referral follow-up

- Identify and train access, assessment and referral staff- for pilot sites/pops

- Identify funding and/or staff resources for pilot to carry out access interviews and assessments, make referrals, manage data system and monitor and evaluate system

- Define Coordinated Assessment duties needed to maintain and enhance system

- Determine process for identifying the entity that will manage the coordinated assessment process and be responsible for future referrals and referral reconciliations

  - Using this process, choose the CA managing entity

- Develop and implement plan and timeline for implementing data sharing between providers and/or develop non-HMIS system for managing coordinated assessment process until data sharing is active for all mandated and participating providers

  - Develop a data map detailing how information will move from one step of the process to the next (Suggest requesting expansion of Cloudburst TA to accomplish this task)

- Develop a public communication plan and promotional material to distribute after pilot

  - Develop a plan that leverages existing communication networks and conveys a consistent message about system access across several channels

- Create a plan for how the Coordinated Assessment will be ‘Switched On”

  - A written plan should be established that includes dates, times, and contingency plans in case of problems

- Implement the pilot

  - Measure and share reports on implementation with Committee and CoCs

- Determine steps needed to implement system Statewide

- Work with funders to change contract language to require participation in Coordinated Assessment process

- Develop a coordinated assessment-specific budget and financial plan

  - Costs should be considered with both CoCs in mind and should be considered when discussing ESG allocations, CoC program applications, CoC reallocation processes, CoC planning dollars, etc.

- Develop plan for ongoing system monitoring and quality improvement adjustments

  - Develop other benchmarks for monitoring performance

- Create a communications plan to notify key partners and stakeholders about how the coordinated assessment system works and their role in making it successful

- Develop and implement internal and external process to review coordinated assessment system function and effectiveness

ACCESS:

- Improve system for shelter providers to refer literally homeless households to each other

- Choose shelter access points

- Determine resources required to successfully implement CA system at each access point

- Determine shelter system diversion and referral protocols for households not entering shelter

- Work with identified access points and consumers to determine protocols

- Determine 211 system protocols for diversion and referral

- Work with OA on cross-referencing 211 system with proposed CA system

- Determine current and projected demand on crisis response system based on available data on client demographics, housing inventory and utilization

- Obtain resources for funding prevention

- Develop written standards for prevention programs

- Develop training for staff at access points

- Explore possibility of longer Release of Information timeframe to coordinate referrals

ASSESS:

- Diversion

- Finalize prevention/diversion questions and request additions and edits to CallPoint content to accommodate changes

- Implement a standardized diversion/prevention tool among homeless system access points

- Determine Housing Barrier Assessment questions using VI-SPDAT questions as base and request inclusion in HMIS

- Implement standardized housing barrier assessment for shelter and outreach workers

- Determine when HMIS UDE’s will be collected

- Determine at what point it should be administered, and by whom

- Develop written protocols for assessment

ASSIGN:

- Promote system-wide Housing First Philosophy

- Housing Prioritization

  - Verify VI-SPDAT inclusion in HMIS and global access plan for all assessment providers

  - Implement VI-SPDAT to assist with housing resource allocation to eligible households

- Develop and implement prioritization policy and procedures for housing resource referrals

- Develop and implement referral system, preferably electronic, to provide household information to matched housing programs for further eligibility screening

- Define referral

- Define process for referral, e.g., definition, steps, responsibilities, acceptance/denial of referrals

- Create waitlist protocols

- Determine prioritization strategy for housing resources beyond LTS initiative

  - Examine implementation of LTS initiative to determine best practices and system improvements

- Provide training to providers on prioritization of HUD-funded housing and the LTS initiative

- Develop process for monitoring and improving accuracy of referrals

- Develop process/functionality for keeping and updating vacancy info in HMIS

- Work with programs to remove admission barriers

- Develop written protocols for Assignment