**FY2016 HUD CoC NOFA Timeline**

**Due September 14, 2016 (Version: 7/8/2016)**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Task** | **Responsibility** | **Date** | **Done** |
| 1 | The Collaborative Applicant (CA) reviews NOFA announcement in its entirety and summarizes it | CA |  |[ ]
| 2 | CA develops project timeline for due dates and gets input from the CoC Committees. | CA | July 8 |[ ]
| 3 | CA sends announcement to new and renewal projects indicating they have 30 days to submit their applications in e-snaps. | CA | 7-15 latest |[ ]
| 4 | CA sends out Con Plan Certifications to all 6 jurisdictions for approvals | CA | 8-15 |[ ]
| 5 | **If applicable** CA submits Amendments to the FY 2016 CoC Program Registration  | CA | None required yet |[ ]
| 6 | NOFA Committee meetings* Review NOFA and work plan and make adjustments
* Determine if CoC will reallocate and how much if reallocation will reduce homelessness (write policies if reallocate)
* Need to develop/revise project review, ranking and selection procedures and PUBLICLY POST
* Establish policy priorities based on the NOFA and local needs including CPD Notice 14-012 (prioritizing people who are CH in PSH)
* Review Board requirements, make recommendations to CoC on the Board & incorporate into governance
* Review & update current governance document (by-laws)
 |  MCOC Steering CommitteePCOC NOFA Com | July 8July 15 |[ ]
| 7 | NOFA Committee meetings* Begin work on Section 1: Coordination & Engagement and Project ranking process
* Finalize Coordinated Entry and Written Standards
* Sections on System Performance
 | Committees  | M: July 18P:July 20 |[ ]
| 8 | HUD releases report that establishes Tier 1 and Tier 2 amounts and PH bonus amount available | HUD  | (Final GIW due 7-22 ) |[ ]
| 9 | CoC meeting* Information about NOFA application including due dates & required tasks
* CoC will need to make decisions on:
	+ CoC Joint Board
	+ CoC Governance
	+ HMIS Joint Governance
	+ Process for CoC review, score and ranking procedures
	+ Process for reallocation
 | Full PCoCFull MCOC | July 20July 21 |[ ]
| 10 | HUD form 2991, Certification of Consistency with the Consolidated Plan forms are due back to CA | Con Plan jurisdictions | (set deadline in letter – again, new projects?) |[ ]
| 11 | NOFA Committee meetings* Adopt Written Standards for order of priority
* Review, Ranking and Scoring Policy and Tools
* Continue work on all Sections
 | Committees |  |[ ]
| 12 | PROJECT APPLICATION REVIEW, SCORING and RANKING: |  | Due Aug 15 at the latest |[ ]
| 14 | CoC review of Project Applications (ensure projects pass both eligibility and threshold review, APR review, including MATCH and that all required attachments are submitted with signed dates from ? ). | Project Committee |  |[ ]
| 15 | Scoring Committee scores & ranks projects, completes ranking sheet and submits to CA for Priority Listing in e-snaps (after CoC approves listing)  | Scoring Committee | Week of 8-22? |[ ]
|  | NOFA Committee Meetings* Review and update CoC By-laws
* Finalize Section 1 Questions
* Begin work on Section 3 and 4 Questions
 |  |  |[ ]
|  | CoC Meeting* Vote on Board of Directors By-Laws
* Vote on CoC By-Laws
* Vote on Order of Priority (HUD Notice CPD 14-012)
* Vote on Coordinated Entry Standards
* Vote on Joint HMIS Governance and HMIS Policies and Procedures
 |  |  |[ ]
|  | NOFA Committee Meetings* Complete remaining Sections
 |  |  |[ ]
| 16 | CoC Meetings:* Vote on the Scoring Committee recommendations and documents via minutes
* Complete unfinished items
 | Full CoC Meetings | P: Aug 17M: Aug 18 |[ ]
| 17 | CoC Notification to all Project ApplicantsPublicly post the Ranking and Scoring Document | Chairs send in writing (e-mail) | Aug 30 at the latest |[ ]
| 18 | Applicants whose project is rejected can appeal the decision by submitting a SOLO application in e-snaps directly | Project applicants |  |[ ]
|  | NOFA Committee* Continue work on remaining Sections (HMIS Team will do HMIS section)
 | Committees |  |[ ]
| 19 | CA completes the Project Priority Listings in e-snaps | CA |  |[ ]
| 20 | COC Meetings (move up a week or more?) vote to approve or designates the NOFA Committee to vote to approve the submission by the CA. | Full CoC |  |[ ]
| 24 | CA finalizes all application attachments and reviews application one final time. | CA |  |[ ]
| 25 | CA Posts all parts of the CoC Consolidated Application on the [www.mainehomelessplanning.org](http://www.mainehomelessplanning.org) website  | CA |  |[ ]
| 26 | CA submits application in e-snaps **at least 1** **day early**  | CA | Sept 13, 2016 |[ ]