| FY 2018 MCOC NOFA Application Review of Action Steps |  |  |  |  | DONE |
| --- | --- | --- | --- | --- | --- |
|  | CA | Consultants | CoC | Committee |  |
| HUD Releases GIW to Collaborative Applicants: |  |  |  |  |  |
| - Usually 2-3 weeks to return DRAFT to HUD. The final version posted on HUD Exchange within 6-8 weeks of the original announcement. | X |  |  |  | ☒ |
| HUD Announces that Registration is open: |  |  |  |  |  |
| - Applicant Profile must be updated in e-snaps. Primary Contact and any other authorized users must be added in e-snaps and HDX and granted appropriate read/write/submit rights. | X |  |  |  | ☒ |
| - Registration must be completed and the ARD must match what is on the HUD Approved GIW | X |  |  |  | ☒ |
| - CoC must vote to approve CA submitting the registration in e-snaps. |  |  | X |  | ☒ |
| - CA submits registration in e-snaps; prints confirmation of submission. | X |  |  |  | ☒ |
| HUD Opens the NOFA Competition (60 days to complete) |  |  |  |  |  |
| - CA reviews announcement in its entirety and summarizes any changes | X |  |  |  | ☒ |
| - CoC needs to determine if they will reallocate and how much |  |  | X |  | ☐ |
| - CA may hire a consultant to assist with some sections of the NOFA. | X | X |  |  | ☒ |
| - CA develops timeline for due dates with input from the NOFA Com. | X |  |  | X | ☒ |
| - CA sends out announcement for New and Renewal projects indicating they have 30 days to submit their applications in e-snaps. | X |  | X |  | ☒ |
| - CoC Project Committee and CA review applications for MATCH, completeness, and to ensure proper attachments are submitted. | X | X |  |  | ☐ |
| - CA releases all applications back to projects with issues or if their budgets do not match the HUD Approved GIW, and gives timeline to resubmit | X |  | X |  | ☐ |
| - CA monitors all timeframes, identifies areas of concern and brings to the NOFA Committee for resolution. | X |  |  | X | ☐ |
| Project Priority Listing |  |  |  |  |  |
| - Project Committee monitors projects (This should already be done). Provides results to Selection Committee |  |  |  | X Project | ☐ |
| - Selection Committee needs to score and rank projects. See NOFA instructions regarding ranking for new projects developed as a result of reallocation or new Planning Grant projects |  | X Facilitated by consultant |  | X Selection | ☐ |
| - CoC needs to vote on the Selection Committee recommendations |  |  | X |  | ☐ |
| - CA enters the project priority rankings in e-snaps on all project applications & attaches the scoring spreadsheet to the full application. | X |  |  |  | ☐ |
| Submission to HUD |  |  |  |  |  |
| - Obtain the Certifications of Approval for Consistency with the Consolidated Plan (need to get one from each jurisdiction) and summarize the project listing by region for each approval. | X | X |  |  | ☐ |
| - Once the application is complete, COC must vote, or designate another body to vote, to Approve submission by the CA. | X |  | X |  | ☐ |
| NOFA Application Sections | CA | Consultants | CoC | Committee |  |
| # 1A1-4. Continuum of Care (CoC) Identification (Name, #, CA, HMIS Lead) | X |  |  |  | ☒ |
| # 1B. Continuum of Care (CoC) Engagement | CA | Consultants | CoC | Committee |  |
| 1B-1. CoC Meeting Participants. For the period from May 1, 2017 to April 30, 2018, using the list below, applicant must: (1) select organizations and persons that participate in CoC meetings; and (2) indicate whether the organizations and persons vote, including selecting CoC Board member Applicant must select Yes, No or Not Applicable for all of the listed organization/person categories in 1B-1. | X |  | X |  | ☒ |
| 1B-1a. Applicants must describe the specific strategy the CoC uses to solicit and consider opinions from organizations and/or persons that have an interest in preventing or ending homelessness. (limit 2,000 characters) |  |  | X | X Resource | ☐ |
| 1B-2. Open Invitation for New Members. Applicants must describe: (1) the invitation process; (2) how the CoC communicates the invitation process to solicit new members; (3) how often the CoC solicits new members; and (4) any special outreach the CoC conducted to ensure persons experiencing homelessness or formerly homeless persons are encouraged to join the CoC. (limit 2,000 characters) |  |  | X | X Resource | ☐ |
| 1B-3. Public Notification for Proposals from Organizations Not Previously Funded. Applicants must describe how the CoC notified the public that it will accept and consider proposals from organizations that have not previously received CoC Program funding, even if the CoC is not applying for new projects in FY 2018, and the response must include the date(s) the CoC publicly announced it was open to proposals. (limit 2,000 characters) |  |  | X |  | ☐ |
| # 1C. Continuum of Care (CoC) Coordination | CA | Consultants | CoC | Committee |  |
| 1C-1. CoCs Coordination, Planning, and Operation of Projects. Applicants must use the chart below to identify the federal, state, local, private, and other organizations that serve individuals, families, unaccompanied youth, persons who are fleeing domestic violence who are experiencing homelessness, or those at risk of homelessness that are included in the CoCs coordination, planning, and operation of projects. Applicant must select Yes, No or Not Applicable for all of the listed organizations in 1C-1. |  |  | X |  | ☐ |
| 1C-2. CoC Consultation with ESG Program Recipients. Applicants must describe how the CoC: (1) consulted with ESG Program recipients in planning and allocating ESG funds; and (2) participated in the evaluating and reporting performance of ESG Program recipients and subrecipients. (limit 2,000 characters) | X |  | X |  | ☐ |
| 1C-2a. Providing PIT and HIC Data to Consolidated Plan Jurisdictions. Did the CoC provide Point-in-Time (PIT) and Housing Inventory Count (HIC) data to the Consolidated Plan jurisdictions within its geographic area? |  |  |  |  | ☐ |
| 1C-2b. Providing Other Data to Consolidated Plan Jurisdictions. Did the CoC provide local homelessness information other than PIT and HIC data to the jurisdiction(s) Consolidated Plan(s)? |  |  |  |  | ☐ |
| 1C-3. Addressing the Safety Needs of Domestic Violence, Dating Violence, Sexual Assault, and Stalking Survivors. Applicants must describe: (1) the CoC’s protocols, including the existence of the CoC’s emergency transfer plan, that prioritizes safety and trauma-informed, victim-centered services to prioritize safety; and (2) how the CoC maximizes client choice for housing and services while ensuring safety and confidentiality. (limit 2,000 characters) |  |  | X |  | ☐ |
| 1C-3a. Applicants must describe how the CoC coordinates with victim services providers to provide annual training to CoC area projects and Coordinated Entry staff that addresses best practices in serving survivors of domestic violence, dating violence, sexual assault, and stalking. (limit 2,000 characters) | X |  | X |  | ☐ |
| 1C-3b. Applicants must describe the data the CoC uses to assess the scope of community needs related to domestic violence, dating violence, sexual assault, and stalking, including data from a comparable database. (limit 2,000 characters) |  |  |  |  | ☐ |
| 1C-4. 1C-4. DV Bonus Projects. Is your CoC applying for DV Bonus Projects? | X |  | X |  | ☐ |
| 1C-5. 1C-5. PHAs within CoC. Applicants must use the chart to provide information about each Public Housing Agency (PHA) in the CoC’s geographic areas: (1) Identify the percentage of new admissions to the Public Housing or Housing Choice Voucher (HCV) Programs in the PHA who were experiencing homelessness at the time of admission; (2) Indicate whether the PHA has a homeless admission preference in its Public Housing and/or HCV Program; and (3) Indicate whether the CoC has a move on strategy. The information should be for Federal Fiscal Year 2017. |  |  | X |  | ☐ |
| 1C-5a. For each PHA where there is not a homeless admission preference in their written policy, applicants must identify the steps the CoC has taken to encourage the PHA to adopt such a policy. (limit 2,000 characters) |  |  |  |  | ☐ |
| 1C-5b. Move On Strategy with Affordable Housing Providers. Does the CoC have a Move On strategy with affordable housing providers in its jurisdiction (e.g., multifamily assisted housing owners, PHAs, Low Income Tax Credit (LIHTC) developments, or local low-income housing programs)? |  |  |  |  | ☐ |
| 1C-6. Addressing the Needs of Lesbian, Gay, Bisexual, Transgender (LGBT). Applicants must describe the actions the CoC has taken to address the needs of Lesbian, Gay, Bisexual, and Transgender individuals and their families experiencing homelessness. (limit 2,000 characters) |  |  |  |  | ☐ |
| 1C-6a. Anti-Discrimination Policy and Training. Applicants must indicate if the CoC implemented a CoC-wide anti-discrimination policy and conducted CoC-wide anti-discrimination training on the Equal Access Final Rule and the Gender Identity Final Rule. 1. Did the CoC implement a CoC-wide anti-discrimination policy that applies to all projects regardless of funding source? 2. Did the CoC conduct annual CoC-wide training with providers on how to effectively implement the Equal Access to Housing in HUD Programs Regardless of Sexual Orientation or Gender Identity (Equal Access Final Rule)? 3. Did the CoC conduct annual CoC-wide training with providers on how to effectively implement Equal Access to Housing in HUD Programs in Accordance with an Individual’s Gender Identity (Gender Identity Final Rule)? Applicant must select Yes or No for all of the listed policies in 1C-6a. |  |  |  |  | ☐ |
| 1C-7. Criminalization of Homelessness. Applicants must select the specific strategies the CoC implemented to prevent the criminalization of homelessness in the CoC’s geographic area. Select all that apply. |  |  |  |  | ☐ |
| 1C-8. Centralized or Coordinated Assessment System. Applicants must: (1) demonstrate the coordinated entry system covers the entire CoC geographic area; (2) demonstrate the coordinated entry system reaches people who are least likely to apply homelessness assistance in the absence of special outreach; (3) demonstrate the assessment process prioritizes people most in need of assistance and ensures they receive assistance in a timely manner; and (4) attach CoC’s standard assessment tool. (limit 2,000 characters) |  |  |  |  | ☐ |
| # 1D. Continuum of Care (CoC) Discharge Planning | CA | Consultants | CoC | Committee |  |
| 1D-1. Discharge Planning–State and Local. Applicants must indicate whether the CoC has a discharge policy to ensure persons discharged from the systems of care listed are not discharged directly to the streets, emergency shelters, or other homeless assistance programs. Check all that apply (note that when "None:" is selected no other system of care should be selected). |  |  | X | SHC | ☒ |
| 1D-2. Discharge Planning Coordination. Applicants must indicate whether the CoC actively coordinates with the systems of care listed to ensure persons who have resided in them longer than 90 days are not discharged directly to the streets, emergency shelters, or other homeless assistance programs. Check all that apply (note that when "None:" is selected no other system of care should be selected). |  |  | X | SHC | ☒ |
| # 1E. Continuum of Care (CoC) Project Review, Ranking, and Selection | CA | Consultants | CoC | Committee |  |
| 1E-1. Project Ranking and Selection. Applicants must indicate whether the CoC used the following to rank and select project applications for the FY 2018 CoC Program Competition: (1) objective criteria; (2) at least one factor related to achieving positive housing outcomes; (3) a specific method for evaluating projects submitted by victim services providers; and (4) attach evidence that supports the process selected. Used Objective Criteria for Review, Rating, Ranking and Section Included at least one factor related to achieving positive housing outcomes Included a specific method for evaluating projects submitted by victim service providers Applicant must select Yes or No for all of the responses in 1E-1. |  |  | X | X Project | ☐ |
| 1E-2. Severity of Needs and Vulnerabilities. Applicants must describe: (1) the specific severity of needs and vulnerabilities the CoC considered when reviewing, ranking, and rating projects; and (2) how the CoC takes severity of needs and vulnerabilities into account during the review, rating, and ranking process. (limit 2,000 characters) |  |  | X | X Project | ☐ |
| 1E-3. Public Postings. Applicants must indicate how the CoC made public: (1) objective ranking & selection process the CoC used for all projects (new & renewal); (2) CoC Consolidated Application–including the CoC Application, Priority Listings, and all projects accepted and ranked or rejected, which HUD required CoCs to post to their websites, or partners websites, at least 2 days before the CoC Program Competition application submission deadline; and (3) attach documentation demonstrating the objective ranking, rating, and selections process and the final version of the completed CoC Consolidated Application, including the CoC Application with attachments, Priority Listing with reallocation forms and all project applications that were accepted and ranked, or rejected (new and renewal) was made publicly available, that legibly displays the date the CoC publicly posted the documents. | X |  | X | X Project | ☐ |
| 1E-4. Reallocation. Applicants must indicate whether the CoC has cumulatively reallocated at least 20 percent of the CoC’s ARD between the FY 2014 and FY 2018 CoC Program Competitions. Reallocation: |  |  | X | X Project | ☐ |
| 1E-5. Local CoC Competition. Applicants must indicate whether the CoC: (1) established a deadline for project applications that was no later than 30 days before the FY 2018 CoC Program Competition Application deadline–attachment required; (2) rejected or reduced project application(s)–attachment required; and (3) notify applicants that their project application(s) were being rejected or reduced, in writing, outside of e-snaps, at least 15 days before FY 2018 CoC Program Competition Application deadline–attachment required. : (1) Did the CoC establish a deadline for project applications that was no later than 30 days before the FY 2018 CoC Program Competition Application deadline? Attachment required. (2) If the CoC rejected or reduced project application(s), did the CoC notify applicants that their project application(s) were being rejected or reduced, in writing, outside of e-snaps, at least 15 days before FY 2018 CoC Program Competition Application deadline? Attachment required. (3) Did the CoC notify applicants that their applications were accepted and ranked on the Priority Listing in writing outside of esnaps, at least 15 before days of the FY 2018 CoC Program Competition Application deadline? | X |  | X | X Project | ☐ |
| # 2A. Homeless Management Information System (HMIS) Implementation | CA | Consultants | CoC | Committee |  |
| 2A-1. Roles and Responsibilities of the CoC and HMIS Lead. Does your CoC have in place a Governance Charter or other written documentation (e.g., MOU/MOA) that outlines the roles and responsibilities of the CoC and HMIS Lead? Attachment Required. | X |  | X | X | ☒ |
| 2A-1a. Applicants must: (1) provide the page number(s) where the roles and responsibilities of the CoC and HMIS Lead can be found in the attached document(s) referenced in 2A-1, and (2) indicate the document type attached for question 2A-1 that includes roles and responsibilities of the CoC and HMIS Lead (e.g., Governance Charter, MOU/MOA). | X |  | X | X | ☐ |
| 2A-2. HMIS Policy and Procedures Manual. Does your CoC have a HMIS Policy and Procedures Manual? Attachment Required. | X |  |  |  | ☒ |
| 2A-3. HMIS Vender. What is the name of the HMIS software vendor? | X |  |  |  | ☒ |
| 2A-4. HMIS Implementation Coverage Area. Using the drop-down boxes, applicants must select the HMIS implementation Coverage area. | X |  |  |  | ☒ |
| 2A-5. Bed Coverage Rate. Using 2018 HIC and HMIS data, applicants must report by project type: (1) total number of beds in 2018 HIC; (2) total beds dedicated for DV in the 2018 HIC; and (3) total number of beds in HMIS. | X |  |  |  | ☒ |
| 2A-5a. To receive partial credit, if the bed coverage rate is 84.99 percent or lower for any of the project types in question 2A-5., applicants must provide clear steps on how the CoC intends to increase this percentage for each project type over the next 12 months. (limit 2,000 characters) | X |  |  |  | ☒ |
| 2A-6. AHAR Shells Submission: How many 2017 Annual Housing Assessment Report (AHAR) tables shells did HUD accept? | X |  |  |  | ☒ |
| 2A-7. CoC Data Submission in HDX. Applicants must enter the date the CoC submitted the 2018 Housing Inventory Count (HIC) data into the Homelessness Data Exchange (HDX). (mm/dd/yyyy) | X |  |  |  | ☒ |
| # 2B. Continuum of Care (CoC) Point-in-Time Count | CA | Consultants | CoC | Committee |  |
| 2B-1. PIT Count Date. Applicants must enter the date the CoC conducted its 2018 PIT count (mm/dd/yyyy). | X |  |  |  | ☒ |
| 2B-2. HDX Submission Date. Applicants must enter the date the CoC submitted its PIT count data in HDX (mm/dd/yyyy). | X |  |  |  | ☒ |
| 2C. Continuum of Care (CoC) Point-in-Time (PIT) Count: Methodologies | CA | Consultants | CoC | Committee |  |
| 2C-1. Change in Sheltered PIT Count Implementation. Applicants must describe any change in the CoC’s sheltered PIT count implementation, including methodology and data quality changes from 2017 to 2018. Specifically, how those changes impacted the CoC’s sheltered PIT count results. (limit 2,000 characters) | X |  |  |  | ☒ |
| 2C-2. Did your CoC change its provider coverage in the 2018 sheltered count? | X |  |  |  | ☒ |
| 2C-2a. If “Yes” was selected in 2C-2, applicants must enter the number of beds that were added or removed in the 2018 sheltered PIT count. | X |  |  |  | ☒ |
| 2C-3. Presidentially Declared Disaster Changes to Sheltered PIT Count. Did your CoC add or remove emergency shelter, transitional housing, or Safe Haven inventory because of funding specific to a Presidentially declared disaster, resulting in a change to the CoC’s 2018 sheltered PIT count? | X |  |  |  | ☒ |
| 2C-3a. If “Yes” was selected for question 2C-3, applicants must enter the number of beds that were added or removed in 2018 because of a Presidentially declared disaster. | X |  |  |  | ☒ |
| 2C-4. Changes in Unsheltered PIT Count Implementation. Did your CoC change its unsheltered PIT count implementation, including methodology and data quality changes from 2017 to 2018? If your CoC did not conduct and unsheltered PIT count in 2018, select Not Applicable. | X |  |  |  | ☒ |
| 2C-5. Identifying Youth Experiencing Homelessness in 2018 PIT Count. Did your CoC implement specific measures to identify youth experiencing homelessness in its 2018 PIT count? | X |  |  |  | ☒ |
| 2C-5.a. Youth details (only pops up if you say yes to 2C-5) |  |  |  |  | ☐ |
| 2C-6. 2018 PIT Implementation. Applicants must describe actions the CoC implemented in its 2018 PIT count to better count: (1) individuals and families experiencing chronic homelessness; (2) families with children experiencing homelessness; and (3) Veterans experiencing homelessness. (limit 2,000 characters) | X |  |  |  | ☐ |
| # 3A. Continuum of Care (CoC) System Performance | CA | Consultants | CoC | Committee |  |
| 3A-1. First Time Homeless as Reported in HDX. In the box below, applicants must report the number of first-time homeless as reported in HDX. | X |  | X |  | ☐ |
| 3A-1a. Applicants must: (1) describe how the CoC determined which risk factors the CoC uses to identify persons becoming homeless for the first time; (2) describe the CoC’s strategy to address individuals and families at risk of becoming homeless; and (3) provide the name of the organization or position title that is responsible for overseeing the CoC’s strategy to reduce the number of individuals and families experiencing homelessness for the first time. (limit 2,000 characters) |  |  |  |  | ☐ |
| 3A-2. Length-of-Time Homeless as Reported in HDX. Applicants must: (1) provide the average length of time individuals and persons in families remained homeless (i.e., the number); (2) describe the CoC’s strategy to reduce the length-of-time individuals and persons in families remain homeless; (3) describe how the CoC identifies and houses individuals and persons in families with the longest lengths of time homeless; and (4) provide the name of the organization or position title that is responsible for overseeing the CoC’s strategy to reduce the length of time individuals and families remain homeless. (limit 2,000 characters) | X |  | X |  | ☐ |
| 3A-3. Successful Permanent Housing Placement and Retention as Reported in HDX. Applicants must: (1) provide the percentage of individuals and persons in families in emergency shelter, safe havens, transitional housing, and rapid rehousing that exit to permanent housing destinations; and (2) provide the percentage of individuals and persons in families in permanent housing projects, other than rapid rehousing, that retain their permanent housing or exit to permanent housing destinations. |  |  |  |  | ☐ |
| 3A-3a. Applicants must: (1) describe the CoC’s strategy to increase the rate at which individuals and persons in families in emergency shelter, safe havens, transitional housing and rapid rehousing exit to permanent housing destinations; and (2) describe the CoC’s strategy to increase the rate at which individuals and persons in families in permanent housing projects, other than rapid rehousing, retain their permanent housing or exit to permanent housing destinations. (limit 2,000 characters) | X |  | X |  | ☐ |
| 3A-4. Returns to Homelessness as Reported in HDX. Applicants must report the percentage of individuals and persons in families returning to homelessness over a 6- and 12-month period as reported in HDX. | X |  | X |  | ☐ |
| 3A-4a. Applicants must: (1) describe how the CoC identifies common factors of individuals and persons in families who return to homelessness; (2) describe the CoC’s strategy to reduce the rate of additional returns to homelessness; and (3) provide the name of the organization or position title that is responsible for overseeing the CoC’s strategy to reduce the rate individuals and persons in families returns to homelessness. (limit 2,000 characters) |  |  |  |  | ☐ |
| 3A-5. Job and Income Growth. Applicants must: (1) describe the CoC’s strategy to increase access to employment and non-employment cash sources; (2) describe how the CoC works with mainstream employment organizations to help individuals and families increase their cash income; and (3) provide the organization name or position title that is responsible for overseeing the CoC’s strategy to increase job and income growth from employment. (limit 2,000 characters) | X |  | X |  | ☐ |
| 3A-6. System Performance Measures Data Submission in HDX. Applicants must enter the date the CoC submitted the System Performance Measures data in HDX, which included the data quality section for FY 2017 (mm/dd/yyyy) | X |  |  | X Resource | ☐ |
| # 3B. Continuum of Care (CoC) Performance and Strategic Planning Objective | CA | Consultants | CoC | Committee |  |
| 3B-1. DedicatedPLUS and Chronically Homeless Beds. In the boxes below, applicants must enter: (1) total number of beds in the Project Application(s) that are designated as DedicatedPLUS beds; and (2) total number of beds in the Project Application(s) that are designated for the chronically homeless, which does not include those that were identified in (1) above as DedicatedPLUS Beds. | X |  |  |  | ☐ |
| 3B-2. Orders of Priority. Did the CoC adopt the Orders of Priority into their written standards for all CoC Program-funded PSH projects as described in Notice CPD-16-11: Prioritizing Persons Experiencing Chronic Homelessness and Other Vulnerable Homeless Persons in Permanent Supportive Housing? Attachment Required. |  |  | X |  | ☐ |
| 3B-2.1. Prioritizing Households with Children. Using the following chart, applicants must check all that apply to indicate the factor(s) the CoC currently uses to prioritize households with children during FY 2018. |  |  | X |  | ☐ |
| 3B-2.2. Applicants must: (1) describe the CoC’s current strategy to rapidly rehouse every household of families with children within 30 days of becoming homeless; (2) describe how the CoC addresses both housing and service needs to ensure families successfully maintain their housing once assistance ends; and (3) provide the organization name or position title responsible for overseeing the CoCs strategy to rapidly rehouse families with children within 30 days of becoming homeless. (limit 2,000 characters) |  |  | X |  | ☐ |
| 3B-2.3. Antidiscrimination Policies. Applicants must check all that apply that describe actions the CoC is taking to ensure providers (including emergency shelter, transitional housing, and permanent supportive housing (PSH and RRH) within the CoC adhere to antidiscrimination policies by not denying admission to or separating any family members from other members of their family or caregivers based on age, sex, gender, LGBT status, marital status, or disability when entering a shelter or housing. | X |  | X |  | ☐ |
| 3B-2.4. Strategy for Addressing Needs of Unaccompanied Youth Experiencing Homelessness. Applicants must indicate whether the CoC’s strategy to address the unique needs of unaccompanied homeless youth includes the following: |  |  | X |  | ☐ |
| 3B-2.5. Prioritizing Unaccompanied Youth Experiencing Homelessness Based on Needs. Applicants must check all that apply from the list below that describes the CoC’s current strategy to prioritize unaccompanied youth based on their needs. |  |  | X | X Youth | ☐ |
| 3B-2.6. Applicants must describe the CoC's strategy to increase: (1) housing and services for all youth experiencing homelessness by providing new resources or more effectively using existing resources, including securing additional funding; and (2) availability of housing and services for youth experiencing unsheltered homelessness by providing new resources or more effectively using existing resources. (limit 3,000 characters) |  |  | X | X Youth | ☐ |
| 3B-2.6a. Applicants must: (1) provide evidence the CoC uses to measure both strategies in question 3B-2.6. to increase the availability of housing and services for youth experiencing homelessness; (2) describe the measure(s) the CoC uses to calculate the effectiveness of the strategies; and (3) describe why the CoC believes the measure it uses is an appropriate way to determine the effectiveness of the CoC’s strategies. (limit 3,000 characters) |  |  |  |  | ☐ |
| 3B-2.7. Collaboration–Education Services. Applicants must describe how the CoC collaborates with: (1) youth education providers; (2) McKinney-Vento State Education Agency (SEA) and Local Education Agency (LEA); (3) school districts; and (4) the formal partnerships with (1) through (3) above. (limit 2,000 characters) |  |  | X |  | ☐ |
| 3B-2.7a. Applicants must describe the policies and procedures the CoC adopted to inform individuals and families who become homeless of their eligibility for education services. (limit 2,000 characters) |  |  |  |  | ☐ |
| 3B-2.8. Does the CoC have written formal agreements, MOU/MOAs or partnerships with one or more providers of early childhood services and supports? Select “Yes” or “No”. Applicants must select “Yes” or “No”, from the list below, if the CoC has written formal agreements, MOU/MOA’s or partnerships with providers of early childhood services and support. |  |  | X | X | ☐ |
| 3B-3.1. Veterans Experiencing Homelessness. Applicants must describe the actions the CoC has taken to identify, assess, and refer Veterans experiencing homelessness, who are eligible for U.S. Department of Veterans Affairs (VA) housing and services, to appropriate resources such as HUD-VASH, Supportive Services for Veterans Families (SSVF) program and Grant and Per Diem (GPD). (limit 2,000 characters) |  |  | X | X Vets | ☐ |
| 3B-3.2. Does the CoC use an active list or by name list to identify all Veterans experiencing homelessness in the CoC? |  |  | X | X Vets | ☐ |
| 3B-3.3. Is the CoC actively working with the VA and VA-funded programs to achieve the benchmarks and criteria for ending Veteran homelessness? |  |  | X | X Vets | ☐ |
| 3B-3.4. Does the CoC have sufficient resources to ensure each Veteran experiencing homelessness is assisted to quickly move into permanent housing using a Housing First approach? |  |  | X | X Vets | ☐ |
| 3B-5. Racial Disparity. Applicants must: (1) indicate whether the CoC assessed whether there are racial disparities in the provision or outcome of homeless assistance; (2) if the CoC conducted an assessment, attach a copy of the summary. |  |  |  |  |  |
| 4A. Continuum of Care (CoC) Accessing Mainstream Benefits and Additional Policies | CA | Consultants | CoC | Committee |  |
| 4A-1. Healthcare. Applicants must indicate, for each type of healthcare listed below, whether the CoC: (1) assists persons experiencing homelessness with enrolling in health insurance; and (2) assists persons experiencing homelessness with effectively utilizing Medicaid and other benefits. |  |  | X |  | ☐ |
| 4A-1a. Mainstream Benefits. Applicants must: (1) describe how the CoC works with mainstream programs that assist persons experiencing homelessness to apply for and receive mainstream benefits; (2) describe how the CoC systematically keeps program staff up-to-date regarding mainstream resources available for persons experiencing homelessness (e.g., Food Stamps, SSI, TANF, substance abuse programs); and (3) provide the name of the organization or position title that is responsible for overseeing the CoC’s strategy for mainstream benefits. (limit 2,000 characters) |  |  | X | X | ☐ |
| 4A-2.Housing First: Applicants must report: (1) total number of new and renewal CoC Program Funded PSH, RRH, SSO non-coordinated entry, Safe-Haven, and Transitional Housing projects the CoC is applying for in FY 2018 CoC Program Competition; and (2) total number of new and renewal CoC Program Funded PSH, RRH, SSO non-coordinated entry, Safe-Haven, and Transitional Housing projects the CoC is applying for in FY 2018 CoC Program Competition that have adopted the Housing First approach–meaning that the project quickly houses clients without preconditions or service participation requirements. | X |  | X | X | ☐ |
| 4A-3. Street Outreach. Applicants must: (1) describe the CoC’s outreach; (2) state whether the CoC's Street Outreach covers 100 percent of the CoC’s geographic area; (3) describe how often the CoC conducts street outreach; and (4) describe how the CoC tailored its street outreach to persons experiencing homelessness who are least likely to request assistance. (limit 2,000 characters) | X |  | X |  | ☐ |
| 4A-4. Affirmative Outreach. Applicants must describe: (1) the specific strategy the CoC implemented that furthers fair housing as detailed in 24 CFR 578.93(c) used to market housing and supportive services to eligible persons regardless of race, color, national origin, religion, sex, gender identify, sexual orientation, age, familial status or disability; and (2) how the CoC communicated effectively with persons with disabilities and limited English proficiency fair housing strategy in (1) above. (limit 2,000 characters) |  |  | X | X | ☐ |
| 4A-5. RRH Beds as Reported in the HIC. Applicants must report the total number of rapid rehousing beds available to serve all household types as reported in the Housing Inventory Count (HIC) for 2017 and 2018. | X |  | X | X | ☐ |
| 4A-6. Rehabilitation or New Construction Costs. Are new proposed project applications requesting $200,000 or more in funding for housing rehabilitation or new construction? | X |  |  |  | ☐ |
| 4A-7. Homeless under Other Federal Statutes. Is the CoC requesting to designate one or more of its SSO or TH projects to serve families with children or youth defined as homeless under other Federal statutes? | X |  |  |  | ☐ |

| 4.B. ATTACHMENTS | Required | Notes | Done |
| --- | --- | --- | --- |
| 1C-5. PHA Administration Plan–Homeless Preference | No |  |  |
| 1C-5. PHA Administration Plan–Move-on Multifamily Assisted Housing Owners' Preference | No |  |  |
| 1C-8. Centralized or Coordinated Assessment Tool | Yes |  |  |
| 1E-1. Objective Critiera–Rate, Rank, Review, and Selection Criteria (e.g., scoring tool, matrix) | Yes |  |  |
| 1E-3. Public Posting CoCApproved Consolidated Application | Yes |  |  |
| 1E-3. Public Posting–Local Competition Rate, Rank, Review, and Selection Criteria (e.g., RFP) | Yes |  |  |
| 1E-4. CoC’s Reallocation Process | Yes |  |  |
| 1E-5. Notifications Outside esnaps– Projects Accepted | Yes |  |  |
| 1E-5. Notifications Outside esnaps– Projects Rejected or Reduced | Yes |  |  |
| 1E-5. Public Posting–Local Competition Deadline | Yes |  |  |
| 2A-1. CoC and HMIS Lead Governance (e.g., section of Governance Charter, MOU, MOA) | Yes |  |  |
| 2A-2. HMIS–Policies and Procedures Manual | Yes |  |  |
| 3A-6. HDX–2018 Competition Report | Yes |  |  |
| 3B-2. Order of Priority–Written Standards | No |  |  |
| 3B-5. Racial Disparities Summary | No |  |  |
| 4A-7.a. Project List–Persons Defined as Homeless under Other Federal Statutes (if applicable) | No |  |  |
| Other |  |  |  |
| Other |  |  |  |