## After Action Review (AAR) for Coordinated Entry

What is an AAR?

- An AAR is a quick reflective exercise during an ongoing initiative, to improve results in the initiative.

- The AAR facilitates learning from experience; it does not require outside experts.

- AARs can be very powerful tools for change, especially if they are repeated at major project milestones.

The AAR is best used to…

- Improve practice: by identifying problems and finding solutions.

- Develop capacity: improve communication, clarify roles and objectives.

- Reflect on significant project moments: when the memory of past actions is fresh.

HOW TO COMPLETE THE AAR:

- Break into groups and introduce yourselves.

- Assign a facilitator.

- Pose the four questions to the group.

- Get opinions from all participants.

- Record all answers and note any trends that emerge.

The Questions:

Question 1: What was supposed to happen in Coordinated Entry?

The answer(s) should be a brief recap of the objectives or intended results. This step is crucial in gauging if all persons involved understood the action(s) to be taken.

Question 2: What actually happened?

Obtain the answer through personal accounts of the participants. Ask participants always to refer to facts that support their conclusions about what happened.

Question 3: Why was there a difference (between the plan and the actual result)?

Discuss and agree on the reasons for the differences. Identify the factors that contributed to success or lack thereof.

Question 4: What will we do next time (the same, and differently)?

You are looking for specific ideas for action that can be implemented.

## Tips for Success:

- Avoid using AAR for evaluating performance or for assigning credit or blame; to do so will likely kill the process.

- During the discussion, focus on issues that are relevant to future activity.

- Make recommendations both actionable and as specific as possible.

- Don’t over-analyze and get bogged down with unnecessary detail; discuss only the most important factors and move along.