## Slide 1: Structured Networking After Action Review (Pause and Learn)
Leah Bruns
November 9,2018

## Slide 2: WHAT IS AN AFTER ACTION REVIEW (AAR)?
An AAR is a quick reflective exercise during an ongoing initiative, to improve results in the initiative.
The AAR facilitates learning from experience; it does not require outside experts.
AARs can be very powerful tools for change, especially if they are repeated at major project milestones

## Slide 3: The AAR is best used to…
Improve practice
  by identifying problems and finding solutions.
Develop capacity
  improve communication, clarify roles and objectives.
Reflect on significant project moments
  when the memory of past actions is fresh.

## Slide 4: REQUIREMENTS:
Facilitator (can also be a participant)
Flipchart
2 - 15 participants
45 minutes

## Slide 5: How to do an AAR
Break into groups and introduce yourselves
Assign a facilitator
Pose the four questions to the group.
Get opinions from all participants
Record all answers and note any trends that emerge.

## Slide 6: Question 1: What was supposed to happen in Coordinated Entry?
The answer(s) should be a brief recap of the objectives or intended results. This step is crucial in gauging if all persons involved understood the action(s) to be taken.

## Slide 7: Question 2: What actually happened?
Obtain the answer through personal accounts of the participants. Ask participants always to refer to facts that support their conclusions about what happened.

## Slide 8: Question 3: Why was there a difference (between the plan and the actual result)?
Discuss and agree on the reasons for the differences. Identify the factors that contributed to success or lack thereof.

## Slide 9: Question 4: What will we do next time (the same, and differently)?
You are looking for specific ideas for action that can be implemented.

## Slide 10: Tips for Success
Avoid using AAR for evaluating performance or for assigning credit or blame; to do so will likely kill the process

## Slide 11: Tips for Success
During the discussion, focus on issues that are relevant to future activity.

## Slide 12: Tips for Success
Reflecting and learning from past actions must be focused on what you will do, or not do differently, in future.

## Slide 13: Tips for Success
Make recommendations both actionable and as specific as possible.

## Slide 14: Tips for Success
Don’t over-analyze and get bogged down with unnecessary detail; discuss only the most important factors and move along.

## Slide 15: What will happen with the information?
The CoC Board and/or the CE Subcommittee will review the responses.

## Slide 16: Questions?

## Slide 17: Response to the AAR
One way AAR data could be used is…
  To create a brief action plan, or simply assign responsibilities for relevant actions, in order to maintain the successes and improve on the shortcomings.

## Slide 18: Tips for Success
The learning from an AAR can be captured in a brief (e.g. 1 page) action plan. If you choose to do so, then keep the writing simple.
In the action plan, maintain confidentiality and do not attribute any comments to specific individuals; this will help maximize openness and trust among participants.