## Sheet1
Priority | Topic/subtopic | Details | 2018 NOFA Q# (if applicable) | Committee or group | Timeframe / deadline | Latest Updates 3-8-19 | October 2019 post application look back | 2020-05-01
High | NOFA Com meets year-round | Reviews NOFA process notes (the Parking Lot) and Application to identify items to be addressed in preparation for the next NOFA, prioritizes and delegates tasks to specific committees (including NOFA Com itself) 12/5- discussion abot scheduling - will keep meeting in Portland on months when Board meets in Portland - recommend shifting to 3rd fridays on months when board meets in Augusta. | All of it | NOFA Com | All year, Ongoing | Need to schedule a meeting in April in anticipation of NOFA | Meeting yr round was helpful - allowed some planning & prep - still losts to so at the end but didn't seem as stressful | Doing it - can we rmove items that have been done?
High | Gaps and Needs Analysis | Comprehensive statewide study of homeless data, resources, and other relevant info with specific focus on subpops (DV, Unaccompanied Youth, Vets, SUD, Families, etc.. 12/5 consultants will present at Jan SCH - Board is invited (and maybe we cancel jan board) | 3B-2.4, 2.5, 2.6., 6a. | Data Com, Res Com, HMIS, TA | several months - start ASAP | Contract in place with HRSI to start very soon. Contact is Terry Camacho-Gonsalves at tcamacho@hsri.org | Got the final - need to review it and set up a plan to implement the recommendations and conduct follow up | We have a Report. It says we need to collect data in order to analyze our gaps and needs. It says some other things too - like that we need more housing. Worth every penny.
High | Roles and Responsibilities | CoC, CA, BOD, Coms, Chairs, HMIS Lead, Projects, Members, partners… who is responsible for what and how do we track and ensure fulfillment of duties 12/5 - Doc Review is working on these | 2A-1. (& entities named in Part 3) |  | a few meetings | Chipping away via new Governance docs | still working on some but we've made progress - new Gov, Com Charters, new Bylaw in the works | Almost done! New Gov, new by-laws, com charters, etc.
High | Coordinated Entry | Covers entire Geography, reaches least likely to apply, prioritization, tools, marketing, connection to housing, not just shelter. 12/5 still paused, developing P&P, no set date yet | 1C-8. | CES Com | All year, Ongoing | Still paused, Good info from Community of Practice TA | I think we are still 'paused' but have made good progress on process and info sharing - need to hit the Play button again and see how it goes | lots of progress on some aspects - still not fully up and running.
HIGH | Homeless Preference & Move-On strategies | Formal policies/MOUs with PHAs (and housing developers?) 12/5 continue to pursue - both to better clarify exisiting docs and work with other PHA's. Move on - not scored this last time but likely to be not only scored but expanded next time | 1C-5 & 5a. | BOD? | Quick. Draft & send letters, follow-up | Need to request/collect any current docs in place - and/or encourage implementing them | We have MOUs with MaineHousing and Portland HA - should send to other HA's as examples and ask them if they wil do the same - and we should try to find a way to tract numbers | Have asked MaineHousing Dev/Asset Mgnt for anything they have. Still need to reach out to other PHAs.
HIGH | Racial Disparity Assessment | Assess whether there are racial disparities in the provision or outcomes of homeless services/housing 12/5 - work with resource com around some sort of training - be prepared to answer more in depth narratives. Chris reports large disparities in the Youth population. Bangor is looking at/working on this - can we expand that statewide? | 3B-5. | ? | need to look at examples | review HUD and HMIS data and develop an 'analysis' and coresponding plan of action | We now have HUD and STELLA reports, and an MCOC statement and Policy in place - what's next? What do we do with this info? | need to look at new data - HMIS/STELLA - we have a statmetn/policy, but need to share that, raise awareness, and figure out what we can do if we find problems
High | CoC & DV coordinated trainings | Emergency Transfer Plans, CE Training coordination re: comparable Db compliance and reporting, scope of need for DV services (ties to Gaps & Needs) There were a lot of new questions in this NOFA about DV Safety, Trainings, CE, Need, etc… above and beyond those specifically related to the DV Bonus projects | 1C-3 & 3a & 3b. | several: Data, Res, CES, NOFA, MCEDV | set up some meetings to assess | This would be a lot easier if either group had a full scale CE up and running. At lease we should meet, discuss, and set up a joint training session on all related topics. | DV providers have a much better Db now and are developing their own (compatible) CE - still need to work on cross training and Emergency Transfer Plans | <same
Med | Annual CoC-wide trainings with providers | How to effectively implement Equal Access Final Rule and Gender Identity Final Rule. | 1C-6, 6a., 3B-2.3. | Res Com | find examples - set a date | Check with Resource Com and ESHAP trainings to see what has been done, or can be done soon | EE/GI training conducted 9-13-19 - live and via GoTo for statewide coverage. Also trainings on Fainr Housing, Ed Rights, Subsidies, SSI/SSDI, VAWA - what can do to ensure compliance? | <<same
Med | Discharge Planning | Review policies and ensure CoC and provider level coordination with these systems, MOUs or other written policies would be good (written by them, not us) | 1D-1 & 2. | Pol Com, BOD, SHC | ? | This has always been a SHC thing - they are reconnecting with Hospitals, DOC, OCFS - now is a good time to review/update all the policies | previous comment still applies | New DOC Blueprint. New YHDP foster youth focus and Portland HA FYI. New FUSE and Recovery Housing efforts
Med | Criminalization of Homelessness | Work with state and local government and law enforcement to ensure laws and policies do criminalize or otherwise punish those without homes | 1C-7. | Pol Com, BOD, SHC | ? | Portland and maybe Bangor were doing some work around this - not sure about anything larger. | same - need to share those examples across the state and find a way to track numbers - how often does this happen, and can we prevent it through education and policy change? | Need some baseline data - Rich H-W was collecting some for SHC regarding # banned from shelters/ trespass. Not sure if we can get any data from law enforcement?
High | Monitoring /Scoring/Ranking | Current Tool does not correspond to the new project app questions. Needs to be objective, measure positive outcomes, include dv specific criteria, be evidence based, look at needs and vulnerabilities. Must be publicly posted so applicants know what they are being monitored/scored on. Reallocation based on eval/performance. | 1E-1, 2, 3.,4, 4a. | Proj Com | All year, Ongoing | Monitoring seems to be going more smoothly, though not really a 'new' process. Need to work on scoring templates and ranking. | Mike and the Com started making some good progress but ended up falling back on the old process because that was the expecation, and monitoring is 'looking back' - we need to clarify the expectation ASAP so we can actually monitor to it next time | looking at examples/processes ofother CoCs. Can we score Renewals - based on monitoring - before the NOFA is even out? (some other CoCs do this). Also - look at gaps and needs to develop a better strategy fo rwhat sorts of NEW projects we need (as opposed to just waiting for HUD to tell us what we can have)
Med | CoC Recruitment & Engagement. | Need to recruit Law Enforcement, Local Jails, Hospitals, School Admin & Liaisons - Need written policies/MOUs with these and other partners. Open invitation to join, ‘special outreach’ for homeless/formerly homeless. RFP targeted to orgs not previously funded. Stipends for self-advocates to encourage participation. | 1B-1, 2, 3. 3B-2.7 | Res Com | All year, Ongoing | ??? | ??? Still need to work on this | Still working on "On-Boarding Packet" at least for new Board members (we have some!) Also have new members, but need to be organized about recruitment.
Med | Consult with ESG recipient and subrecipients. | Planning and allocation of ESG funds. Participate in evaluation and reporting performance of ESG recipients and subrecipients | 1C-2. | ?Proj Com, Data Com, BOD | several meetings | ESG recipients would be MaineHousing and Portland - Ptld came to BOD to dicuss proposed budget changes - need to formally discuss ESHAP with MaineHousing. Ask Mike to bring shelter monitoring info to both Proj Com and full MCOC | still room for improvement | Pretty well covered - consultation is part of Consolidated Plan process, rule making, and RFP development now.
Low | Provide PIT, HIC and other ‘local’ data to all Con Plan jurisdictions | We do post, and respond to requests, but we should simply slice and dice the information and send it to them, whether or not they want it or use it. | 1C-2a & b. | Data Com, HMIS | Quick, once data is compiled. Draft & send. | compiling data now | need to systematically distribut to all ConPlanCert jurisdictions, even if they don't ask for it or need it | <same - can start with the 2020 data once finalized
High | PIT sheltered and unsheltered methodology | Largely unchanged for past couple of years, but our unsheltered count was way down in 2018. We need to do better recruiting volunteers – instilling enthusiasm, and looking at ways to simplify and streamline data collection. Check boxes limit options but write in answers are sometimes difficult or impossible to use | 2C-4, 5, 6. | Data Com | ASAP if to be part of 2019 | not sure if anything was done to improve unsheltered efforts this year. Need to sort out the Warming Center questions and incorporated them in the PIT. | our volunteer efforts are slipping away - need to revitalize this somehow - do we want ot explore using an app? Or does our size not justify the extra cost? | HMIS sheltered portion is very good. DV is very good. Some non-HMIS projects are good about PIT/HIC. Need to work with other non-hmis agencies. Most importantly, we need to totally re-thing unsheltered approach.
Med | HMIS Bed Coverage rates. Who is responsible for tring to get non-hmis agencies to participate? Is it the HMIS Lead, Data Com, Resource Com… | ES HMIS Bed Coverage is down to 86.27% - (85 is the threshold for needing to explain ourselves). We need to try to get nonparticipating shelters in HMIS. We need a better way to track fluctuation in bed inventory over time. New data standards expect 'real time' inventory data | 2A-5. 2C-2, 2a. | Data Com, HMIS, Res Com? | all year, Ongoing | need updated HIC data to know where we are at now - with a few more non-HMIS beds we may be below the line | we still managed to stay above threshold for ES, (86.11%) but it’s closer - need to try to get some new shelters on board with HMIS. | We are still just above the line - but could easily slip below (For ES) if just one or two more non-participating projects open up.
Med | SPMs | Risk factors for 1st time homeless, addressing those at risk. For 1st time homeless we used measure 5.2. Need to actually tabulate the reasons/factors for 1st time homelessness and analyze why and what we can do to prevent/reduce those. | 3A -1. | Data Com, HMIS | ? | need to review NOFA and Clyde's reports - are we doing any better? | Stella makes these accessible - we need to dig into them and make some decisions based on what we find | <same
Med | SPMs | Job and income growth, work with mainstream employment orgs. Volunteering/Commuity Service is now asked about too. Our Non-cash increases are pretty good buyt we need to work on earned income - there's gotta be something we can do. Our Exits to PH are still low, likely due at least in part to to the number of shelter exits without a destination. Our PH retention is great. Our Returns to Homelessness are pretty good. | 3A-5. | Res Com | All year, Ongoing | same | This was a new area of focus in the NOFA - we got some MOU's - now we need to follow though and spread that info | <same
Med | SPMs | Prioritize/ Rapidly rehouse households with children - need to reduce LOTH | 3B-2.2 | Pol Com, Proj Com | ? | same | most of our efforts have been on LTSs - need to branch out | <same
HIGH | Selection of Selection Committee members | ie protocol, advertising, conflict of interest description, and description of the committee responsibilities |  |  |  | need to start a list of potential recruits soon | new conflict of interest paperwork is good - still need better recruitment | Amy's contract with MaineHousing is up soon. Need someone to take charge of this.
HIGH | Score card | Analysis of the current score card and discussion as whether to "keep" or look for other best practices |  |  |  | Project Com is busy Monitoring - we may need to assign Scoring Template development to another group | better, but still mostly based on old ones - need to totally re-vamp this | <same
HIGH | NOFA priorities | How do we determine as a COC what current priorities are and how they impact scoring |  |  |  | Look at last NOFA results and info from Gaps and Needs - base priorities on the data, not on speculation | look to Gaps and Needs | <same
NEW | Youth | establish gaps/needs specific to Youth and prioritization for providing housing and/or services = prepare of incorporating YHDP initiatives into MCOC processes. We should revamp and recirulate the McKinney Vento Liaison flyers and pamphlets we did a few years back. And try to reconnect with DOE - might have better luck now. |  | Youth Provider Group, YAB | ongoing |  | need to know if projects will be CoC renewals - if not, that's ok, but if they expect CoC funding later, they need to factor that into the design from the start | <same
NEW | Effective communication with individuals with disabilites | This appeared in many of the NOFA questions - I think we answered it well enough, but what can we do better? | [5 empty] | <same
NEW | Reallocation | We are not getting all the projects we ask for - new, renewal, or even bonus. We ARE reallocating - by default - not thoughfully or plannfully. No one wants to say "We are not going fund your project this year." but we have grown comfortable saying "Your project ended up at or near the bottom of Tier 2, and may not be funded by HUD this year." as if we, collectively, have no control over that. | [5 empty] | <same
Anything NEW that we need to add?