| Date | Task | Notes |
| --- | --- | --- |
| June 22 | Supplemental NOFO posted |  |
| June 28/29 | HUD webinars: General/Rural Focus |  |
| July 7 | Board sets local timeline and priorities | MCOC Board Mtg |
| Wk of July13 | Local RFP issued/Plan Team- outline |  |
| July 21 | Scoring tools developed/CoC app work | MCOC Mtg |
| Wk of July 25 | Local scoring & ranking tools posted |  |
| Aug 4 | Applicant info developed/ CoC app work | MCOC Board Mtg |
| Wk of Aug 8 | Local Applicant’s Conference - virtual |  |
| Aug 18 | Plan Team - Draft reviewed by MCOC | MCOC Mtg |
| Wk of Aug 22 | Focus on CoC level app & attachments |  |
| Sept 1 | Plan Team - Final draft approved by Board | MCOC Board Mtg |
| Sept 5 | Local apps due /send ConPlan Certs-2wks |  |
| Wk of Sept 5 | Local apps scored and ranked |  |
| Sept 15 | MCOC approves scoring/ranking | MCOC Mtg |
| Wk of Sept 19 | Projects notified of results/ appeals | (Sept 20 is 30 days prior to submission) |
| Oct 6 | 1st appeals– chairs/2nd appeal - Board | MCOC Board Mtg |
| Wk of Oct 10 | Final review and assembly of app |  |
| Oct. 20 | Final Submission Deadline | MCOC Meeting |